## Modules
Module | Task | Difficulty | Responsible | Is Done | [Admin] | Hien | 1 | OK
[Admin] | Admin manages Universities | 3 | Vinh | OK | [Algorithm] | Khoa | 2 | YES
[Admin] | Admin manages Examinations | 3 | Vinh | OK | [Candidate] | Tri | 3
[Admin] | Admin manages UniExams | 3 | Hien |  | [Charity] | Tuan | 4
[Admin] | Admin manages Categories | 3 | Tuan | OK | [Google Maps] | Vinh | 5
[Admin] | Admin manages Posts | 3 | Tuan |  | [Sponsor]
[Algorithm] | Auto auto suggest Routes (with some creterias) | 5 | Khoa |  | [System]
[Algorithm] | Auto assign Student into Rooms (with some creterias) | 5 | Khoa |  | [User]
[Algorithm] | Auto assign Students to Vehicle | 4 | Khoa |  | [Volunteer]
[Algorithm] | Manual assign Student into Rooms | 3 | Khoa
[Algorithm] | Manual assign Students to Vehicle | 3 | Khoa
[Algorithm] | Manual edit Routes | 4 | Khoa
[Candidate] | Candidate manages their JoinIn | 3 | Hien
[Charity] | Charity manages their CE | 3 | Vinh | OK
[Charity] | Charity manages Lodges of thier CE | 3 | Vinh
[Charity] | Charity manages Cars of their CE | 3 | Vinh
[Charity] | Charity views Volunteers of their CE | 3 | Hien
[Charity] | Charity views Candidates of their CE | 3 | Hien
[Google Maps] | Display Routes | 5 | Hien
[Google Maps] | Display Venues, Lodges | 5 | Tri
[Sponsor] | Sponsor manages their Funds | 3 | Tuan | OK
[Sponsor] | Sponsor manages their Lodges | 3 | Tuan
[Sponsor] | Sponsor manages their Cars | 3 | Hien | OK
[System] | Authentication and authorization | 3 | Tri | OK
[System] | Master page and Admin master page | 3 | Tri
[System] | Auto get news from webs | 3 | Tri
[User] | Registration | 3 | Tri | OK
[User] | Login / Logout | 2 | Tri | OK
[User] | User manages their Profile | 2 | Tri
[User] | User manages their Posts | 4 | Vinh
[User] | User comments and replies comment | 3 | Tuan
[User] | User comment, like, share on Facebook | 4 | Tuan
[User] | User share on Google Plus | 2 | Tuan
[Volunteer] | Volunteer manages their JoinIn | 3 | Tuan

## Issues
Module | Issue | Solution | Asked by | Answered by | Approved | [Admin] | Hien | 1 | OK
[6 empty] | [Algorithm] | Khoa | 2 | YES
[6 empty] | [Candidate] | Tri | 3
[6 empty] | [Charity] | Tuan | 4
[6 empty] | [Google Maps] | Vinh | 5
[Sponsor]
[System]
[User]
[Volunteer]

## UC
Assign
| Admin | Manage Banner | Add | 1 | VinhTNK
|  |  | Edit | 2 | TuanND
|  |  | Delete | 3
|  | Manage Exam Information | Search | 4 | HienNV
|  |  | Add | 5 | VinhTNK
|  |  | Edit | 6 | TuanND
|  |  | Delete | 7
|  | Manage News | Search | 8 | HienNV
|  |  | Add | 9 | VinhTNK
|  |  | Edit | 10 | TuanND
|  |  | Delete | 11
|  | Manage User | Search | 12 | HienNV
|  |  | Add | 13 | VinhTNK
|  |  | Edit | 14 | TuanND
|  |  | Delete | 15
|  | View System Statistics |  | 16
2 | Authorized User | View News |  | 17
|  | Search Charity Information |  | 18 | HienNV
|  | View Map |  | 19
|  | Search Resource |  | 20 | HienNV
|  | View Statistics |  | 21
|  | Comment |  | 22
|  | Edit Profile |  | 23 | TuanND
|  | Logout |  | 24
6 | Candidate | Manage Candidate Request | Make request | 25 | VinhTNK
|  |  | Edit Request | 26 | TuanND
|  |  | Delete Request | 27
|  | View Schedule |  | 28
|  | Search Resource |  | 29 | HienNV
4 | Charity | Manage Information of Charity | Add | 30 | VinhTNK
|  |  | Edit | 31 | TuanND
|  |  | Delete | 32
|  | Manage Request | Make request | 33 | VinhTNK
|  |  | Edit Request | 34 | TuanND
|  |  | Delete Request | 35
|  | Manage Resource | Search | 36 | HienNV
|  |  | Add | 37 | VinhTNK
|  |  | Edit | 38 | TuanND
|  |  | Delete | 39
|  | Manage Schedule | Search | 40 | HienNV
|  |  | Add | 41 | VinhTNK
|  |  | Edit | 42 | TuanND
|  |  | Delete | 43
|  | Pay Fees |  | 44
|  | View Charity Statistics |  | 45
3 | Guest | Register |  | 46
3 | Guest and Authorized User | Search Charity Information |  | 47 | HienNV
|  | Search Resources |  | 48 | HienNV
|  | View Map |  | 49
|  | View News |  | 50
|  | View Statistics |  | 51
1 | UnAuthorized | Login |  | 52
5 | Sponsor | Manage Sponsor Resource | TransferMoney | 53
|  |  | Add Sponsor Resource | 54 | VinhTNK
|  |  | Edit Sponsor Resource | 55 | TuanND
|  |  | Delete Sponsor Resource | 56
|  | Search Charities |  | 57 | HienNV
|  | View Sponsor Statistics |  | 58 | HienNV
7 | Volunteer | Manage News | Search | 59 | HienNV
|  |  | Add | 60 | VinhTNK
|  |  | Edit | 61 | TuanND
|  |  | Delete | 62
|  | View Request |  | 63
|  | View Schedule |  | 64